## Sheet1
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contingency Plan | Responsible | Status | Last modified date
1 | Technical | Technical issues with Unity engine | 1 | 10 | 10 | Regular testing and updates of Unity engine | Number of bugs discovered during testing | Switch to an alternative engine | Lukas | Open | 2023-04-17
2 | Technical | Difficulty integrating artwork | 3 | 5 | 15 | Work closely with the designer to ensure compatibility | Number of successfully integrated assets | Adjust art style to accommodate compatibility issues | Nico | Open | 2023-04-17
3 | Resources | Insufficient resources to complete game | 4 | 9 | 36 | Prioritize tasks and focus on core gameplay mechanics | Number of completed tasks vs. timeline | Remove unnesessary features from the backlog | Johannes | Open | 2023-04-17
4 | Gameplay | Inadequate instructions for gameplay | 1 | 3 | 3 | Conduct user testing and gather feedback | Number of players intuitive understanding the game | Create tutorial based on feedback | Tim | Open | 2023-04-17
5 | Schedule | Time delays due to unforeseen events | 4 | 6 | 24 | Build extra time into schedule and prioritize tasks | Timeliness of completed tasks | Re-evaluate project timeline and adjust as necessary | Paul | Open | 2023-04-17
6 | Technical | Incompatibility with Android-versions | 3 | 8 | 24 | Conduct regular compatibility testing on Android devices / different versions | Number of compatibility issues discovered during testing | Adjust code to ensure compatibility | Johannes | Open | 2023-04-17